## Slide 1: CLEANSTONE
Kick-off meeting
Main administrative tasks
www.interreg.net
Udine, 17th December 2019

## Slide 2
2
Support to LP in WP1 Activities
Jan Zerjal
contributi@euroservis.eu

## Slide 3
3
Reporting
Changes
Communication duties
Main Administrative tasks

## Slide 4
Main Administrative tasks Reporting
4
PP sends all the documentation about the incurred costs
Sends FLC’s report to LP
Collects all the reports and asks MA for reinbursmet
Checks over the cost and documentation, sends a report to each PP
Checks and transmits to CA for reimbursement
Certifies the costs and pays the reimbursement

## Slide 5
Main Administrative tasks Reporting
5
PP sends all the documentation about the incurred costs
Sends FLC’s report to LP
Collects all the reports and asks MA for reinbursmet
Checks over the cost and documentation, sends a report to each PP
Checks and transmits to CA for reimbursement
Certifies the costs and pays the reimbursement

## Slide 6
Main administrative tasks Reporting
Reporting on Cohemon
Staff costs
Overheads (15% of staff costs)
Travel costs (max 148€ Italia, 132 Austria for each night stay; no less than 50€ for each reporting period)
External expertise and services (market research, over 5.000€ at least three quotations, best value for money!)
Equipment costs (market research, over 5.000€ at least three quotations, best value for money!)
For more detailed information:
IT-DE: http://www.interreg.net/downloads/V3_FFR_NdaS_V_IT-AT.pdf
IT: http://www.interreg.net/downloads/453827_ITAT_-_Rendicontazione_IT_v2.pdf
DE: http://www.interreg.net/downloads/453826_ITAT_-_Abrechnung_DE_v2.pdf

## Slide 7
Main Administrative tasks Reporting
7
PP sends all the documentation about the incurred costs
Sends FLC’s report to LP
Collects all the reports and asks MA for reimbursement
Checks over the cost and documentation, sends a report to each PP
Checks and transmits to CA for reimbursement
Certifies the costs and pays the reimbursement
Up to three months

## Slide 8
Main Administrative tasks Reporting
8
PP sends all the documentation about the incurred costs
Sends FLC’s report to LP
Collects all the reports and asks MA for reimbursement
Checks over the cost and documentation, sends a report to each PP
Checks and transmits to CA for reimbursement
Certifies the costs and pays the reimbursement

## Slide 9
9
Reporting deadlines
Annual Reports: every year By 31th January
Requests for reimbursement presented to MA at least once per year by the 30th of October
Main Administrative tasks Reporting

## Slide 10
10
Annual Report 2019
LP must present a report containing:
A description of the activities carried out during 2019
A description of the achieved outputs in 2019
The progress of the expenditure for each PP in 2019
A forecast of expenditure at 30 June 2020 and at 31th October 2020 for each PP
Main Administrative tasks Reporting

## Slide 11
11
Annual Report 2019 – Things to do!
By 15 January 2020 every PP must send to LP:
A brief description of the activities carried out during 2019
The total costs incurred in 2019
A forecast of reported expenditure at 30 June 2020 and at 31th October 2020
Main Administrative tasks Reporting

## Slide 12
12
The 2019 spending goal
Main Administrative tasks Reporting
Partner | 2019 spending goal
LP | €5.825,00
PP1 | €3.743,75
PP2 | €3.316,25
PP3 | €5.937,50
PP4 | €2.023,71
Total | €20.846,21

## Slide 13
Main Administrative tasks Reporting
13
PP sends all the documentation about the incurred costs
Sends FLC’s report to LP
Collects all the reports and asks MA for reimbursement
Checks over the cost and documentation, sends a report to each PP
Checks and transmits to CA for reimbursement
Certifies the costs and pays the reimbursement
How often? When?

## Slide 14
14
Main Administrative tasks Reporting

## Slide 15
17
Main Administrative tasks Changes
Duration Changes
LP asks MA for any kind of changes in project duration
Budget changes
Budget changes can be done by swapping amounts between cost categories, none of these changes can affect project results

## Slide 16
18
Main Administrative tasks Changes
Budget changes (swaps in cost categories)
For changes below 20% of PP’s budget and under €10.000 PP communicates the change to MA via Cohemon.
For Changes over 20% of PP’s budget and over €10.000 MA approval is needed, PP must communicate to LP and Local Authority the need of a budget shift and LP will ask MA for the permission.

## Slide 17
19
Main Administrative tasks Communication
Minimal compulsory communications
Dedicated page on your website
Display a poster in , at least, A3 format in your operational headquarters

## Slide 18
20
Main Administrative tasks Communication
Communication duties
In every project communication output ( letters, attendance sheets, communications, social media posts, gadgets, web pages, press articles…) the official Programme and EU logos should be used
You can find manuals for the usage of the Programme and Eu logo, and prest materials (as this PPT) under the “communication” menu here:
IT http://www.interreg.net/it/570.asp
DE http://www.interreg.net/de/570.asp

## Slide 19
Main Administrative tasks
In case of any doubts please to ask your local Authority or LP for help.
You can write to me anytime
contributi@euroservis.eu
21

## Slide 20: Thank you, for you attention
www.interreg.net